## Sheet1
NO | DATE | DESCRIPTION | WBS | COST CODE | AMOUNT | REMARKS
1 | 2023-02-01 | Expenses | Budget | E00 | 94300000
2 | 2023-03-01 | Expenses | Budget | E00 | 19890000
3 | 2023-04-01 | Expenses | Budget | E00 | 27390000
4 | 2023-05-01 | Expenses | Budget | E00 | 19890000
5 | 2023-06-01 | Expenses | Budget | E00 | 19890000
6 | 2023-07-01 | Expenses | Budget | E00 | 27390000
7 | 2023-08-01 | Expenses | Budget | E00 | 19890000
8 | 2023-09-01 | Expenses | Budget | E00 | 22890000
9 | 2023-02-01 | Expenses | Budget | M00 | 0
10 | 2023-03-01 | Expenses | Budget | M00 | 0
11 | 2023-04-01 | Expenses | Budget | M00 | 0
12 | 2023-05-01 | Expenses | Budget | M00 | 0
13 | 2023-06-01 | Expenses | Budget | M00 | 0
14 | 2023-07-01 | Expenses | Budget | M00 | 0
15 | 2023-08-01 | Expenses | Budget | M00 | 0
16 | 2023-09-01 | Expenses | Budget | M00 | 0
17 | 2023-02-01 | Expenses | Budget | P00 | 62000000
18 | 2023-03-01 | Expenses | Budget | P00 | 70000000
19 | 2023-04-01 | Expenses | Budget | P00 | 87500000
20 | 2023-05-01 | Expenses | Budget | P00 | 70000000
21 | 2023-06-01 | Expenses | Budget | P00 | 70000000
22 | 2023-07-01 | Expenses | Budget | P00 | 70000000
23 | 2023-08-01 | Expenses | Budget | P00 | 70000000
24 | 2023-09-01 | Expenses | Budget | P00 | 110833333
25 | 2023-02-01 | Expenses | Budget | S00 | 1027280083
26 | 2023-03-01 | Expenses | Budget | S00 | 442958684
27 | 2023-04-01 | Expenses | Budget | S00 | 1013087643
28 | 2023-05-01 | Expenses | Budget | S00 | 5472976893
29 | 2023-06-01 | Expenses | Budget | S00 | 1256403428
30 | 2023-07-01 | Expenses | Budget | S00 | 40657723
31 | 2023-08-01 | Expenses | Budget | S00 | 196635546
32 | 2023-09-01 | Expenses | Budget | S00 | 0
33 | 2023-05-04 | M 16 (5/8") x 400 | Estimate At Completion | EAC | 130425
34 | 2023-05-04 | M 22 (7/8") x 570 | Estimate At Completion | EAC | 333000
35 | 2023-05-04 | M 30 (1 1/4") x 820 | Estimate At Completion | EAC | 771450
36 | 2023-04-09 | SNI MS BJTS420B Ulir D10 x 12 mtr (lurus) | Estimate At Completion | EAC | 27110723.25
37 | 2023-04-09 | SNI MS BJTS420B Ulir D16 x 12 mtr (lurus) | Estimate At Completion | EAC | 73602990
38 | 2023-05-15 | Pekerjaan Installation PT Quantum | Estimate At Completion | EAC | 600000000
39 | 2023-06-26 | Pekerjaan Installation PT Quantum | Estimate At Completion | EAC | 250000000
40 | 2023-07-15 | Pekerjaan Installation PT Quantum | Estimate At Completion | EAC | 533009947.25
41 | 2023-08-26 | Pekerjaan Installation PT Quantum | Estimate At Completion | EAC | 749029841.75
42 | 2023-03-01 | Insurance | Estimate At Completion | EAC | 10775193
43 | 2023-03-01 | Site Management and Establishment | Estimate At Completion | EAC | 0
44 | 2023-04-01 | Contractor Equipments, include Mobilization and Demobilization | Estimate At Completion | EAC | 82500000
45 | 2023-04-01 | Contractor Employee, include mobilization and Demobilization | Estimate At Completion | EAC | 120000000
46 | 2023-04-01 | Contractor Storage Sheds | Estimate At Completion | EAC | 5000000
47 | 2023-04-01 | Contractor Site Office and other Site Accomodation | Estimate At Completion | EAC | 0
48 | 2023-04-01 | Construction Water Supply | Estimate At Completion | EAC | 5000000
49 | 2023-04-01 | Construction Electrical Power Supply | Estimate At Completion | EAC
50 | 2023-04-01 | Safety, Health and Welfare of Work People | Estimate At Completion | EAC | 10000000
51 | 2023-03-01 | House Keeping , Removal of Rubbish, Removal Of Spoil and Surplus Material from the site | Estimate At Completion | EAC | 20000000
52 | 2023-04-01 | Project Administration, Reporting, and Meeting | Estimate At Completion | EAC | 15000000
53 | 2023-03-01 | Shop Drawing | Estimate At Completion | EAC | 0
54 | 2023-03-01 | As Built Drawing | Estimate At Completion | EAC | 0
55 | 2023-08-01 | Testing Of Materials | Estimate At Completion | EAC | 25000000
56 | 2023-08-01 | Setting Out The Works | Estimate At Completion | EAC
57 | 2023-03-01 | Insurance | Estimate At Completion | EAC | 25000000
58 | 2023-08-01 | Site Management and Establishment | Estimate At Completion | EAC | 168292416
59 | 2023-08-01 | Contractor Equipments, include Mobilization and Demobilization | Estimate At Completion | EAC | 55000000
60 | 2023-08-01 | Contractor Employee, include mobilization and Demobilization | Estimate At Completion | EAC | 10000000
61 | 2023-08-01 | Contractor Storage Sheds | Estimate At Completion | EAC | 12000000
62 | 2023-08-01 | Contractor Site Office and other Site Accomodation | Estimate At Completion | EAC | 50000000
63 | 2023-08-01 | Construction Water Supply | Estimate At Completion | EAC | 22500000
64 | 2023-08-01 | Construction Electrical Power Supply | Estimate At Completion | EAC | 25000000
65 | 2023-08-01 | Safety, Health and Welfare of Work People | Estimate At Completion | EAC | 40000000
66 | 2023-03-01 | House Keeping , Removal of Rubbish, Removal Of Spoil and Surplus Material from the site | Estimate At Completion | EAC | 20000000
67 | 2023-08-01 | Project Administration, Reporting, and Meeting | Estimate At Completion | EAC | 25000000
68 | 2023-03-01 | Shop Drawing | Estimate At Completion | EAC | 24000000
69 | 2023-03-01 | As Built Drawing | Estimate At Completion | EAC | 14000000
70 | 2023-08-01 | Testing Of Materials | Estimate At Completion | EAC | 5000000
71 | 2023-03-01 | Setting Out The Works | Estimate At Completion | EAC | 5000000
72 | 2023-02-01 | Bore Pile | Estimate At Completion | EAC | 520000000
73 | 2023-02-01 | Soil Disposal | Estimate At Completion | EAC | 9780232
74 | 2023-02-01 | Concrete Fe'= 30 Mpa (Cement Type - 1) | Estimate At Completion | EAC | 115553282
75 | 2023-02-01 | Deform Bar D10 | Estimate At Completion | EAC | 54491518
76 | 2023-02-01 | Deform Bar D16 | Estimate At Completion | EAC | 175800154
77 | 2023-02-01 | Cutting Pile | Estimate At Completion | EAC | 10800000
78 | 2023-02-01 | PDA Test | Estimate At Completion | EAC | 45000000
79 | 2023-02-01 | PIT Test | Estimate At Completion | EAC | 30000000
80 | 2023-02-09 | Soil Excavation | Estimate At Completion | EAC | 12654927
81 | 2023-02-09 | Soil Back Fill | Estimate At Completion | EAC | 4408768
82 | 2023-02-09 | Soil Disposal | Estimate At Completion | EAC | 2916174
83 | 2023-02-09 | Compacted Soil | Estimate At Completion | EAC | 1046955
84 | 2023-02-09 | Conventional formwork | Estimate At Completion | EAC | 64095683
85 | 2023-02-09 | Leveling Concrete Fe'= 10 Mpa (Cement Type - | Estimate At Completion | EAC | 2286590
86 | 2023-02-09 | Concrete Fe'= 30 Mpa (Cement Type - 1) | Estimate At Completion | EAC | 53597537
87 | 2023-02-09 | Deform Bar D10 | Estimate At Completion | EAC | 16977904
88 | 2023-02-09 | Deform Bar D16 | Estimate At Completion | EAC | 43341939
89 | 2023-02-09 | Deform Bar D19 | Estimate At Completion | EAC | 47763678
90 | 2023-02-09 | Anchorbolt (AB M30) | Estimate At Completion | EAC | 169872000
91 | 2023-02-09 | Grouting | Estimate At Completion | EAC | 793083
92 | 2023-02-17 | Soil Excavation | Estimate At Completion | EAC | 17544249
93 | 2023-02-17 | Soil Back Fill | Estimate At Completion | EAC | 5413137
94 | 2023-02-17 | Soil Disposal | Estimate At Completion | EAC | 5260039
95 | 2023-02-17 | Conventional formwork | Estimate At Completion | EAC | 82373467
96 | 2023-02-17 | Leveling Concrete Fe'= 1O Mpa (Cement Type - | Estimate At Completion | EAC | 4750819
97 | 2023-02-17 | Cone「ete Fe'= 30 Mpa (Cement Type - 1) | Estimate At Completion | EAC | 56251162
98 | 2023-02-17 | Deform Bar D10 | Estimate At Completion | EAC | 32336658
99 | 2023-02-17 | Deform Bar D13 | Estimate At Completion | EAC | 7933492
100 | 2023-02-17 | Deform Bar D19 | Estimate At Completion | EAC | 81415360
101 | 2023-02-01 | Bore Pile | Estimate At Completion | EAC | 302400000
102 | 2023-02-01 | Soil Disposal | Estimate At Completion | EAC | 12214500
103 | 2023-02-01 | Concrete Fe'= 30 Mpa (Cement Type - 1) | Estimate At Completion | EAC | 122145000
104 | 2023-02-01 | Deform Bar D10 | Estimate At Completion | EAC | 40903195
105 | 2023-02-01 | Deform Bar D16 | Estimate At Completion | EAC | 131961600
106 | 2023-02-01 | Cutting Pile | Estimate At Completion | EAC | 1350000
107 | 2023-02-01 | PDA Test | Estimate At Completion | EAC | 24000000
108 | 2023-02-01 | PIT Test | Estimate At Completion | EAC | 16000000
109 | 2023-02-09 | Soil Excavation | Estimate At Completion | EAC | 11466000
110 | 2023-02-09 | Soil Back Fill | Estimate At Completion | EAC | 8309600
111 | 2023-02-09 | Soil Disposal | Estimate At Completion | EAC | 6918800
112 | 2023-02-09 | Compacted Soil | Estimate At Completion | EAC | 3903900
113 | 2023-02-09 | Conventional Formwork | Estimate At Completion | EAC | 42410500
114 | 2023-02-09 | Leveling Concrete F0=10 Mps(Cement Type -1) | Estimate At Completion | EAC | 1950000
115 | 2023-02-09 | Concrete Fo=30 Mps (Cement Type -1) | Estimate At Completion | EAC | 56655000
116 | 2023-02-09 | Deform Bar D10 | Estimate At Completion | EAC | 12744195
117 | 2023-02-09 | Deform Bar D16 | Estimate At Completion | EAC | 32533940
118 | 2023-02-09 | Deform Bar D19 | Estimate At Completion | EAC | 35853048
119 | 2023-02-09 | Anchor Bolt (A8 M30) | Estimate At Completion | EAC | 28800000
120 | 2023-02-09 | Grouting | Estimate At Completion | EAC | 4025000
121 | 2023-02-17 | Soil Excavation | Estimate At Completion | EAC | 15895971
122 | 2023-02-17 | Soil Back Fill | Estimate At Completion | EAC | 10202624
123 | 2023-02-17 | Soil Disposal | Estimate At Completion | EAC | 12481568
124 | 2023-02-17 | Conventional Formwork | Estimate At Completion | EAC | 54505450
125 | 2023-02-17 | Leveling Concrete F0=10 Mps(Cement Type -1) | Estimate At Completion | EAC | 4051491
126 | 2023-02-17 | Concrete Fo=30 Mps (Cement Type -1) | Estimate At Completion | EAC | 63424000
127 | 2023-02-17 | Deform Bar D10 | Estimate At Completion | EAC | 24273000
128 | 2023-02-17 | Deform Bar D13 | Estimate At Completion | EAC | 5955150
129 | 2023-02-17 | Deform Bar D19 | Estimate At Completion | EAC | 61113150
130 | 2023-03-03 | Compacted Soil | Estimate At Completion | EAC | 56307900
131 | 2023-03-03 | Base Coerse 100 mm and Compacted CBR 50% | Estimate At Completion | EAC | 21755750
132 | 2023-03-03 | Plastic Sheet | Estimate At Completion | EAC | 6910515
133 | 2023-03-03 | Concrete Fo=30 Mps (Cement Type -1) | Estimate At Completion | EAC | 163808000
134 | 2023-03-03 | Conventional Formwork | Estimate At Completion | EAC | 4977500
135 | 2023-03-03 | Wire Mesh M8 @150 , double layer | Estimate At Completion | EAC | 107496900
136 | 2023-03-03 | Expantion Joint | Estimate At Completion | EAC | 1260000
137 | 2023-03-17 | Steel Dark Floor 0.75mm Thk | Estimate At Completion | EAC | 53597370
138 | 2023-03-17 | Concrete Fc'= 30 Mps (Cement Type -1) | Estimate At Completion | EAC | 26377440
139 | 2023-03-17 | Conventional Formwork | Estimate At Completion | EAC | 1142419
140 | 2023-03-17 | Wire Mesh M8 @150 , double layer | Estimate At Completion | EAC | 38154060
141 | 2023-03-31 | Steel Dark Floor 0.75mm Thk | Estimate At Completion | EAC | 53835000
142 | 2023-03-31 | Concrete Fc'= 30 Mps (Cement Type -1), use admixture integral waterproofing with Crystaline type Brand: ex Sika Control - 230 WT | Estimate At Completion | EAC | 79675800
143 | 2023-03-31 | Conventional Formwork | Estimate At Completion | EAC | 5263500
144 | 2023-03-31 | Wire Mesh M8 @150 | Estimate At Completion | EAC | 70736400
145 | 2023-03-31 | Concrete Floor Coating, Master Protect 200, 150 Micron thk | Estimate At Completion | EAC | 69985500
146 | 2023-03-31 | Polyunehane Curving along tank bundwall on EL +17900, Ucrete RG, Ex.MBCC (BASF) | Estimate At Completion | EAC | 2087472
147 | 2023-04-21 | H-400x200x8x13 (Length = 296,06 m) | Estimate At Completion | EAC | 520685968
148 | 2023-04-21 | H-300x150x6.5x9 (Length = 159,39 m) | Estimate At Completion | EAC | 163008846
149 | 2023-04-21 | H-500x200x10x16 (Length = 251,25 m) | Estimate At Completion | EAC | 609447482
150 | 2023-04-21 | H-200x100x5.5x8 (Length = 233,92 m) | Estimate At Completion | EAC | 181995991
151 | 2023-04-21 | H-400x400x13x21 (Length = 128,4 m) | Estimate At Completion | EAC | 676166400
152 | 2023-04-21 | H-350x350x12x19 (Length = 75,4 m) | Estimate At Completion | EAC | 220911600
153 | 2023-04-21 | H-100x100x6x3 (Length = 197,81 m) | Estimate At Completion | EAC | 121499469
154 | 2023-04-21 | H-200x200x8x12 (Length = 31,5 m) | Estimate At Completion | EAC | 74107488
155 | 2023-04-21 | 2L-60x60x5 (Length = 150.34 m) | Estimate At Completion | EAC | 43161300
156 | 2023-04-21 | Round Bar 0-16 (Length = 138,57 m) | Estimate At Completion | EAC | 5977062
157 | 2023-04-21 | 2L-70x70x6 (Length = 76,65m) | Estimate At Completion | EAC | 30466800
158 | 2023-04-21 | H-150x150x7x10 (Length = 9.9 m) | Estimate At Completion | EAC | 21348600
159 | 2023-04-21 | C-200x90x8x13,5 (Length = 112,45 m) | Estimate At Completion | EAC | 97351800
160 | 2023-04-21 | H-150x75x5x7 (Length = 607,64 m) | Estimate At Completion | EAC | 209795586
161 | 2023-04-21 | LC-150x65x20x3.2 (Length = 922.74 m) | Estimate At Completion | EAC | 241523100
162 | 2023-04-21 | Connection Plate | Estimate At Completion | EAC | 899242890
163 | 2023-04-21 | HS BOLT M14 | Estimate At Completion | EAC
164 | 2023-04-21 | HS BOLT M16 | Estimate At Completion | EAC | 112980000
165 | 2023-04-21 | HS BOLT M20 | Estimate At Completion | EAC | 51648000
166 | 2023-04-21 | HS BOLT M22 | Estimate At Completion | EAC | 19950000
167 | 2023-04-21 | HS BOLT M24 | Estimate At Completion | EAC | 37040000
168 | 2023-04-21 | HS BOLT M27 | Estimate At Completion | EAC | 0
169 | 2023-04-21 | Painting ,Primer and lop coet | Estimate At Completion | EAC | 693420000
170 | 2023-04-21 | Checkend Plate 4.5 mm thk, Hot Dip Galvanized | Estimate At Completion | EAC | 178903750
171 | 2023-04-21 | Grating Galvanized 32mm Thnk (Stair) MSG Type | Estimate At Completion | EAC | 26544000
172 | 2023-04-21 | Handraill Steel Pipe, Hot Dip Galvanized | Estimate At Completion | EAC | 177940000
173 | 2023-04-21 | Railing Steel Pipe, Hot Dip Galvanized (Roof Top) | Estimate At Completion | EAC | 49445000
174 | 2023-04-21 | STEEL BEMPER | Estimate At Completion | EAC
175 | 2023-04-21 | Steel Pipe 4" Sch 40 | Estimate At Completion | EAC | 38496000
176 | 2023-04-21 | Connection Plate | Estimate At Completion | EAC | 2644510
177 | 2023-04-21 | Painting | Estimate At Completion | EAC | 5635000
178 | 2023-05-05 | Brick Masonry , both sides plastered 1 = 15mm | Estimate At Completion | EAC | 53381200
179 | 2023-05-05 | Sandwich Panel 100 mm Thk | Estimate At Completion | EAC | 281411450
180 | 2023-05-05 | Colorbond Corruparted Sheet 0.45 Thk BMT | Estimate At Completion | EAC | 257400000
181 | 2023-05-05 | Flashing Metal Colorbond Sheet 0.45 Thk BMT | Estimate At Completion | EAC | 74190050
182 | 2023-05-19 | Colorbond Corruparted Sheet 0.45 Thk BMT | Estimate At Completion | EAC | 96120000
183 | 2023-05-19 | Cutter Metal Colorbond Sheet 0.45 Thk BMT | Estimate At Completion | EAC | 3928500
184 | 2023-05-19 | Roof Drain - PVC Pipe 4" | Estimate At Completion | EAC | 2490000
185 | 2023-05-19 | Standart down PVC Pipe 4" diameter | Estimate At Completion | EAC | 27540000
186 | 2023-05-19 | Turbine Ventilator 0-24" | Estimate At Completion | EAC | 30000000
187 | 2023-06-02 | Glass fibre Reinforced Cement Board 6 mm Thk First With Paint | Estimate At Completion | EAC | 30038000
188 | 2023-06-16 | Epoxy Roor Hardener, Dry Shake floor hardener 5kg/m2, medium duty, master top BASF | Estimate At Completion | EAC | 195221910
189 | 2023-06-16 | Pedestrian Outdoor Paving Block thickness 80mm, K400 | Estimate At Completion | EAC | 19575000
190 | 2023-06-30 | Aondic emulation paint (for exterior) | Estimate At Completion | EAC | 11337600
191 | 2023-06-30 | Vynil ecetance for interior | Estimate At Completion | EAC | 9448000
192 | 2023-07-14 | D-01 Sincle Swing Door (2100x1000 mm) | Estimate At Completion | EAC | 67050000
193 | 2023-07-14 | L-01 Louvre | Estimate At Completion | EAC | 44700000
194 | 2023-01-26 | Sidding & Girt | Estimate At Completion | EAC | 80000000
195 | 2023-09-30 | Anchor Bolt M20 x 240 Black | Estimate At Completion | EAC | 9504000
196 | 2023-09-30 | CNP 100x50x20x2,3 | Estimate At Completion | EAC | 3596000
197 | 2023-09-30 | UNP 125x65x6x8 | Estimate At Completion | EAC | 6061000
198 | 2023-09-30 | Besi Beton M12 (Saqrod) | Estimate At Completion | EAC | 6780000
199 | 2023-09-30 | Stud Bolt M22x140 (set welding) | Estimate At Completion | EAC | 96660000
200 | 2023-09-30 | Jarum Kertas M16 | Estimate At Completion | EAC | 3150000
201 | 2023-09-30 | OS Bolt M10 - Black | Estimate At Completion | EAC | 11340000
202 | 2023-09-30 | OS Bolt M12x45 (Untuk Star Tresd) - Black | Estimate At Completion | EAC | 18000000
203 | 2023-09-30 | Chemical Ancor M12x160 injection chemical type, ex Sika | Estimate At Completion | EAC | 87120000